## Overview
PepsiCo Demand Forecasting — Roadmap (Task 0 -> 18)
Phase | Tasks | Focus
Foundations | Tasks 0-1 | Scaffold + problem framing + synthetic data
Understand & prepare | Tasks 2-3 | EDA + leakage-free feature pipeline
Baselines | Task 4 | Local baselines = the bar + eval harness
Deep-learning ladder | Tasks 5-10 | MLP -> RNN/LSTM/GRU -> Seq2Seq+Attn -> TCN -> TFT -> probabilistic
Selection & scale | Tasks 11-12 | HPO + champion selection + hybrid refinement
Productionize | Tasks 13-16 | Export -> serve -> deploy -> monitor
Deliver | Tasks 17-18 | Demo app + LLM layer + portfolio deck
Total tasks | 19 (Task 0 -> 18)
Progress | 1 done, 1 next, 17 planned
Where it runs | Local-first on the Mac (DL via PyTorch MPS); cloud optional for scale / real deploy.
Data | Synthetic-primary (channel-aware); Kaggle M5 as an optional real-data benchmark (Task 11).
Architecture | Evidence-driven: Local baseline -> Global model -> per-market comparison -> Hybrid refinement.
See also | Task0_Summary.xlsx (scope/brands/channels/architecture) and TechStack.xlsx.

## Roadmap
Roadmap — Task 0 to 18
Task | Name | Objective | Core DL concept | Engineering skill | Runs on | Status
0 | Foundations & environment | Reproducible, industry-standard project skeleton (no models yet). | — (tooling) | Project layout, env isolation, linting, testing, VCS | Mac | Done
1 | Problem framing & synthetic data (DVC) | Turn business pain into an ML spec; build a high-realism, channel-aware synthetic dataset. | Forecast task formulation; DGP design | Data modeling, DVC, pydantic schema, DuckDB/SQL | Mac | Next
2 | EDA & time-series understanding | Build intuition for the signal before modeling. | Seasonality, stationarity, exogenous drivers | Reproducible notebooks, plotting | Mac | Planned
3 | Data pipeline & feature engineering | Deterministic raw -> model-ready tensors, leakage-free. | Windowing, categorical embeddings, leakage-free splits | ETL as code, config (pydantic/Hydra), unit tests | Mac | Planned
4 | Local baselines & eval harness | Per-market baselines = the bar to beat, plus the scoring machinery everything reuses. | Why baselines matter; backtesting | Metrics, backtesting, MLflow | Mac | Planned
5 | MLP forecaster (first neural net) | Cross into DL with the simplest network. | MLPs, backprop, regularization, LR scheduling | Lightning module, checkpointing, sweeps | Mac (MPS) | Planned
6 | RNN -> LSTM -> GRU | Model temporal dependencies explicitly. | Recurrence, gating, vanishing/exploding gradients | MPS training discipline, reproducibility | Mac (MPS) | Planned
7 | Seq2Seq + Attention | Multi-step-ahead (28d) forecasting done right. | Seq2seq, attention, exposure bias | Attention viz, training-strategy experiments | Mac (MPS) | Planned
8 | Temporal Convolutional Networks (TCN) | A convolutional alternative to recurrence. | Causal/dilated convolution, receptive field, residuals | Architecture ablation, param/FLOP budgeting | Mac (MPS) | Planned
9 | Transformer / TFT (global model) | State-of-the-art attention model; test global vs local per market. | Self-attention, multi-head, entity embeddings, global vs local | pytorch-forecasting, market-level comparison | Mac (MPS) / Cloud (opt) | Planned
10 | Probabilistic & specialized models | Forecast distributions and handle intermittent demand. | Probabilistic forecasting, quantiles, intermittency | Calibration, model-family comparison | Mac (MPS) | Planned
11 | Tracking, HPO & model selection | Pick the champion scientifically; optional real-data reality check. | HPO, bias/variance, model selection | Optuna, experiment hygiene, decision docs | Mac / Cloud (opt) | Planned
12 | Training-as-code + hybrid refinement | Train the champion reproducibly; test hybrid architectures. | Segmented globals, fine-tuning, reconciliation | Training-as-code, architecture selection by backtest | Mac (MPS) / Cloud (opt) | Planned
13 | Export & optimization | Make the model portable and fast for CPU serving. | Graph export, quantization, train/serve skew | ONNX Runtime, perf benchmarking, packaging | Mac | Planned
14 | Serving API (FastAPI + Docker) | A real inference service. | Inference-time preprocessing, interval outputs | API design, containerization, security, testing | Mac (Docker) | Planned
15 | Cloud deployment + CI/CD | A live public endpoint with automated delivery. | — (production readiness) | Cloud deploy, CI/CD, Kubernetes, secrets | Cloud + Mac (local k8s) | Planned
16 | Monitoring, drift & retraining | Keep the model honest in production. | Distribution shift, model decay, retraining cadence | Observability, scheduling, model registry | Mac (docker-compose) / Cloud | Planned
17 | Demo app + LLM insight layer | A stakeholder-facing experience. | Communicating uncertainty; LLM-in-the-loop | App UX, prompt design/testing, integration | Mac + Cloud | Planned
18 | Docs, presentation & portfolio | Package the whole journey for reviewers/recruiters. | Synthesis — where each model family wins/loses | Technical writing, presentation, storytelling | Mac | Planned

## Task Flows
Task Flows & Deliverables — Task 0 to 18
Task | Name | Key sub-steps (flow) | Deliverable
0 | Foundations & environment | Repo + src/ layout; Python 3.12 venv; pyproject deps; ruff+black+pre-commit; pytest smoke; Makefile; git + push to personal GitHub. | Green scaffold + repo pushed
1 | Problem framing & synthetic data (DVC) | Problem spec (28d horizon, WRMSSE); canonical schema geo->channel->retailer->store->SKUxday; per-market calendars; DGP generator (trend/seasonality/promos/weather/intermittency/cold-start/hierarchy/noise); write Parquet; DVC-track; tests. | Versioned synthetic dataset + generator + spec
2 | EDA & time-series understanding | Distributions, intermittency; STL decomposition; ACF/PACF; promo/holiday/weather effects; channel & hierarchy analysis; feature hypotheses. | EDA notebook + findings doc
3 | Data pipeline & feature engineering | Long format; lags/rolling/calendar/price/promo/weather features; channel/retailer/brand embedding prep; time-based splits + rolling-origin CV; windowing; PyTorch Dataset/DataLoader; (Spark local for scale). | Feature pipeline + tests
4 | Local baselines & eval harness | WRMSSE + MAE/RMSE/MAPE/sMAPE/WAPE; naive/seasonal-naive/ETS/ARIMA/SARIMAX/Prophet/VAR/LightGBM/XGBoost; rolling-origin backtest; MLflow tracking; per-market leaderboard. | Leaderboard v1 + reusable eval module
5 | MLP forecaster (first neural net) | Feed-forward over flattened window + embeddings; PyTorch Lightning loop (loss/optimizer/early-stop/LR schedule); dropout/weight-decay; compare vs baselines. | MLP model + leaderboard update
6 | RNN -> LSTM -> GRU | Vanilla RNN (see vanishing gradients) -> LSTM -> GRU; packing, teacher forcing; lookback ablation; gradient clipping; seeds. | Recurrent models + comparison writeup
7 | Seq2Seq + Attention | Encoder-decoder; teacher forcing vs free-running; add attention + visualize weights; recursive vs direct multi-step. | Seq2seq+attention model + attention plots
8 | Temporal Convolutional Networks (TCN) | Dilated causal convolutions; receptive-field math; residual blocks; kernel/dilation ablation; compare to LSTM (speed/accuracy). | TCN model + tradeoff notes
9 | Transformer / TFT (global model) | Positional encoding; self-attention; Temporal Fusion Transformer (static/known-future/observed inputs) with market/channel/retailer/brand/SKU embeddings; variable-selection & attention interpretability; per-market comparison vs baselines. | TFT model + interpretability report
10 | Probabilistic & specialized models | DeepAR intervals; quantile/pinball loss; N-BEATS/N-HiTS; Croston/Tweedie for intermittency; PyMC/NumPyro Bayesian; interval calibration/coverage checks. | Probabilistic models + calibration report
11 | Tracking, HPO & model selection | Optuna sweeps on top architectures; MLflow compare (WRMSSE + intervals + latency); champion + challenger decision; OPTIONAL M5 (Kaggle) real-data benchmark. | model_selection.md + final leaderboard
12 | Training-as-code + hybrid refinement | Training CLI (Hydra config); segmented globals (Beverages vs Snacks / by channel); geography fine-tuning; hierarchical reconciliation (MinT); mixed precision; checkpoint/resume; architecture chosen by backtest. | Production model artifact + train.py
13 | Export & optimization | Export to TorchScript/ONNX + verify parity; dynamic/int8 quantization (latency vs accuracy); package preprocessing + model into one inference class. | CPU-fast model bundle
14 | Serving API (FastAPI + Docker) | FastAPI /predict (28d forecast + intervals) & /health; pydantic schemas; validation + error handling; JWT/OAuth2 auth; Dockerize (slim CPU image); integration tests. | Working container serving predictions
15 | Cloud deployment + CI/CD | Push image to registry (GHCR); deploy to non-Apple cloud (Cloud Run / Render); GitHub Actions (lint/test/build/deploy, emulate locally with `act`); single-node Kubernetes (kind/minikube) demo; smoke-test the live URL. | Live endpoint URL + green CI pipeline
16 | Monitoring, drift & retraining | Log predictions vs actuals; rolling WRMSSE; data/concept drift (Evidently/alibi-detect); alert thresholds; scheduled retraining + registry promotion; Prometheus + Grafana dashboard. | Monitoring dashboard + retraining runbook
17 | Demo app + LLM insight layer | Streamlit app (forecast chart + intervals, filters market/channel/brand, what-if price/promo); optional React build (HTML mockup already done); LLM narrative layer (Claude API) crafted with the prompt-engineering skill; deploy. | Deployed Streamlit demo
18 | Docs, presentation & portfolio | Polish README (architecture diagram, results, live links); MODEL_EVOLUTION.md; Keynote-HTML deck; demo walkthrough; final leaderboard + honest limitations. | Portfolio-ready repo + shareable HTML deck